|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |

|  |
| --- |
| **South Western Sydney - Aged Care****2019/20 - 2023/24****Activity Summary View** |

 |  |  |
|  |  |  |  |
|  |

|  |
| --- |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |

|  |
| --- |
| **AC-EI - 3 - AC 3 - Early Intervention** |

 |  |

 |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Metadata** |

 |  |

 |
|  |
| **Applicable Schedule \***  |
| Aged Care |
| **Activity Prefix \***  |
| AC-EI |
| **Activity Number \*** |
| 3 |
| **Activity Title \***  |
| AC 3 - Early Intervention |
| **Existing, Modified or New Activity \***  |
| New Activity |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Priorities and Description** |

 |  |

 |
|  |
| **Program Key Priority Area \***  |
| Aged Care |
| **Other Program Key Priority Area Description**  |
|  |
| **Aim of Activity \***  |
| Commission early interventions targeted at older people with chronic conditions to reduce avoidable hospitalisations and reduce need to enter extended care, through healthy ageing at home initiatives. |
| **Description of Activity \***  |
| Consultation with community and service providers to identify gaps and needs in health and social services for older people in SWS region. Develop co-design to commission services that will enable healthy ageing at home. Commission services to support healthy ageing. |
| **Needs Assessment Priorities \*** |
| **Needs Assessment** |
| SWSPHN Needs Assessment 2022-2025 |
| **Priorities** |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| **Priority** | **Page reference** |
| Aged Care and Palliative Care | 150 |

 |  |

 |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Demographics** |

 |  |

 |
|  |
| **Target Population Cohort**  |
| - People aged 65 years and over.- Aboriginal and Torres Strait Islander people 50 years and older. |
| **In Scope AOD Treatment Type \*** |
|  |
| **Indigenous Specific \*** |
| No |
| **Indigenous Specific Comments**  |
|  |
| **Coverage**  |
| **Whole Region**  |
| Yes |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Consultation and Collaboration** |

 |  |

 |
|  |
| **Consultation**  |
| SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, , community aged care services / residential aged care services and relevant PHN teams (Digital Health). |
| **Collaboration**  |
| Activities in Aged and Palliative Care are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services and other key stakeholders as necessary. |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Milestone Details/Duration** |

 |  |

 |
|  |
| **Activity Start Date**  |
| 31/12/2021 |
| **Activity End Date**  |
| 30/01/2025 |
| **Service Delivery Start Date** |
| 01/07/2022 |
| **Service Delivery End Date** |
|  |
| **Other Relevant Milestones** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Commissioning** |

 |  |

 |
|  |
| **Please identify your intended procurement approach for commissioning services under this activity:**  |
| **Not Yet Known:** No**Continuing Service Provider / Contract Extension:** No**Direct Engagement:** Yes**Open Tender:** No**Expression Of Interest (EOI):** No**Other Approach (please provide details):** No |
|  |
| **Is this activity being co-designed?**  |
| No |
| **Is this activity the result of a previous co-design process?**  |
| No |
| **Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?**  |
| No |
| **Has this activity previously been co-commissioned or joint-commissioned?**  |
| No |
| **Decommissioning**  |
| No |
| **Decommissioning details?**  |
|  |
| **Co-design or co-commissioning comments**  |
|  |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Planned Expenditure** |

 |  |

 |
|  |
| **Planned Expenditure** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** |
| Early Intervention - Interest |  |  |  |  |  |
| Early Intervention |  |  |  |  |  |

 |  |
|  |  |

 |
| **Totals** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** | **Total** |
| Early Intervention - Interest |  |  |  |  |  |  |
| Early Intervention |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

 |  |

 |
|  |
| **Funding From Other Sources - Financial Details** |
|  |
| **Funding From Other Sources - Organisational Details** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Summary of activity changes for Department** |

 |  |

 |
|  |
| **Activity Status** |
| Ready for Submission |
|  |
|

|  |  |  |
| --- | --- | --- |
|  |  |  |
|  |

|  |
| --- |
|  |

 |  |

 |

 |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |

|  |
| --- |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |

|  |
| --- |
| **AC-VARACF - 1 - AC 1 - Virtual access in RACFs** |

 |  |

 |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Metadata** |

 |  |

 |
|  |
| **Applicable Schedule \***  |
| Aged Care |
| **Activity Prefix \***  |
| AC-VARACF |
| **Activity Number \*** |
| 1 |
| **Activity Title \***  |
| AC 1 - Virtual access in RACFs |
| **Existing, Modified or New Activity \***  |
| New Activity |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Priorities and Description** |

 |  |

 |
|  |
| **Program Key Priority Area \***  |
| Aged Care |
| **Other Program Key Priority Area Description**  |
|  |
| **Aim of Activity \***  |
| To increase the capacity of SWS residential aged care facilities (RACFs) to provide virtual health service delivery. |
| **Description of Activity \***  |
| Identify eligible RACFs to improve and install digital technology to enable virtual health service delivery. |
| **Needs Assessment Priorities \*** |
| **Needs Assessment** |
| SWSPHN Needs Assessment 2022-2025 |
| **Priorities** |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| **Priority** | **Page reference** |
| Aged Care and Palliative Care | 150 |

 |  |

 |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Demographics** |

 |  |

 |
|  |
| **Target Population Cohort**  |
| - People aged 65 years and over.- Aboriginal and Torres Strait Islander people 50 years and older. |
| **In Scope AOD Treatment Type \*** |
|  |
| **Indigenous Specific \*** |
| No |
| **Indigenous Specific Comments**  |
|  |
| **Coverage**  |
| **Whole Region**  |
| Yes |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Consultation and Collaboration** |

 |  |

 |
|  |
| **Consultation**  |
| SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, , community aged care services / residential aged care services and relevant PHN teams (Digital Health). |
| **Collaboration**  |
| Activities in Aged and Palliative Care are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services and other key stakeholders as necessary. |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Milestone Details/Duration** |

 |  |

 |
|  |
| **Activity Start Date**  |
| 31/12/2021 |
| **Activity End Date**  |
| 30/01/2025 |
| **Service Delivery Start Date** |
| 01/07/2022 |
| **Service Delivery End Date** |
|  |
| **Other Relevant Milestones** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Commissioning** |

 |  |

 |
|  |
| **Please identify your intended procurement approach for commissioning services under this activity:**  |
| **Not Yet Known:** No**Continuing Service Provider / Contract Extension:** No**Direct Engagement:** Yes**Open Tender:** No**Expression Of Interest (EOI):** No**Other Approach (please provide details):** No |
|  |
| **Is this activity being co-designed?**  |
| No |
| **Is this activity the result of a previous co-design process?**  |
| No |
| **Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?**  |
| No |
| **Has this activity previously been co-commissioned or joint-commissioned?**  |
| No |
| **Decommissioning**  |
| No |
| **Decommissioning details?**  |
|  |
| **Co-design or co-commissioning comments**  |
|  |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Planned Expenditure** |

 |  |

 |
|  |
| **Planned Expenditure** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** |
| Virtual Access in RACFs - Interest |  |  |  |  |  |
| Virtual Access in RACFs |  |  |  |  |  |

 |  |
|  |  |

 |
| **Totals** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** | **Total** |
| Virtual Access in RACFs - Interest |  |  |  |  |  |  |
| Virtual Access in RACFs |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

 |  |

 |
|  |
| **Funding From Other Sources - Financial Details** |
|  |
| **Funding From Other Sources - Organisational Details** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Summary of activity changes for Department** |

 |  |

 |
|  |
| **Activity Status** |
| Ready for Submission |
|  |
|

|  |  |  |
| --- | --- | --- |
|  |  |  |
|  |

|  |
| --- |
|  |

 |  |

 |

 |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |

|  |
| --- |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |

|  |
| --- |
| **AC-AHARACF - 2 - AC 2 - After Hours access in RACFs** |

 |  |

 |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Metadata** |

 |  |

 |
|  |
| **Applicable Schedule \***  |
| Aged Care |
| **Activity Prefix \***  |
| AC-AHARACF |
| **Activity Number \*** |
| 2 |
| **Activity Title \***  |
| AC 2 - After Hours access in RACFs |
| **Existing, Modified or New Activity \***  |
| New Activity |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Priorities and Description** |

 |  |

 |
|  |
| **Program Key Priority Area \***  |
| Aged Care |
| **Other Program Key Priority Area Description**  |
|  |
| **Aim of Activity \***  |
| Support improvement in after-hours service delivery to RACFs. |
| **Description of Activity \***  |
| To complete audits of RACF procedures for referral to After Hour services, including which services are used and how clinical documentation is completed. |
| **Needs Assessment Priorities \*** |
| **Needs Assessment** |
| SWSPHN Needs Assessment 2022-2025 |
| **Priorities** |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| **Priority** | **Page reference** |
| Aged Care and Palliative Care | 150 |

 |  |

 |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Demographics** |

 |  |

 |
|  |
| **Target Population Cohort**  |
| - People aged 65 years and over.- Aboriginal and Torres Strait Islander people 50 years and older. |
| **In Scope AOD Treatment Type \*** |
|  |
| **Indigenous Specific \*** |
| No |
| **Indigenous Specific Comments**  |
|  |
| **Coverage**  |
| **Whole Region**  |
| Yes |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Consultation and Collaboration** |

 |  |

 |
|  |
| **Consultation**  |
| SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, , community aged care services / residential aged care services and relevant PHN teams (Digital Health). |
| **Collaboration**  |
| Activities in Aged and Palliative Care are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services and other key stakeholders as necessary. |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Milestone Details/Duration** |

 |  |

 |
|  |
| **Activity Start Date**  |
| 31/12/2021 |
| **Activity End Date**  |
| 30/01/2025 |
| **Service Delivery Start Date** |
| 01/07/2022 |
| **Service Delivery End Date** |
|  |
| **Other Relevant Milestones** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Commissioning** |

 |  |

 |
|  |
| **Please identify your intended procurement approach for commissioning services under this activity:**  |
| **Not Yet Known:** No**Continuing Service Provider / Contract Extension:** No**Direct Engagement:** Yes**Open Tender:** No**Expression Of Interest (EOI):** No**Other Approach (please provide details):** No |
|  |
| **Is this activity being co-designed?**  |
| No |
| **Is this activity the result of a previous co-design process?**  |
| No |
| **Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?**  |
| No |
| **Has this activity previously been co-commissioned or joint-commissioned?**  |
| No |
| **Decommissioning**  |
| No |
| **Decommissioning details?**  |
|  |
| **Co-design or co-commissioning comments**  |
|  |
|  |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Activity Planned Expenditure** |

 |  |

 |
|  |
| **Planned Expenditure** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** |
| After Hours Access in RACFs - Interest |  |  |  |  |  |
| After Hours Access in RACFs |  |  |  |  |  |

 |  |
|  |  |

 |
| **Totals** |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Funding Stream** | **FY 20 21** | **FY 21 22** | **FY 22 23** | **FY 23 24** | **FY 24 25** | **Total** |
| After Hours Access in RACFs - Interest |  |  |  |  |  |  |
| After Hours Access in RACFs |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

 |  |

 |
|  |
| **Funding From Other Sources - Financial Details** |
|  |
| **Funding From Other Sources - Organisational Details** |
|  |
|  |
|  |
|

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |

|  |
| --- |
| **Summary of activity changes for Department** |

 |  |

 |
|  |
| **Activity Status** |
| Ready for Submission |
|  |
|

|  |  |  |
| --- | --- | --- |
|  |  |  |
|  |

|  |
| --- |
|  |

 |  |

 |

 |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  |

|  |
| --- |
|  |

 |  |