|  | South Western Sydney - NMHSPA Bilateral PHN Program 2025/26 - 2028/29 Activity Summary View. |  |  |
| --- | --- | --- | --- |
|  | NAB-PRCG - 4 - Regional Commissioning and Governance... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-PRCG. Activity Number *. 4. Activity Title *. Regional Commissioning and Governance. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Other (please provide details). Other Program Key Priority Area Description. Regional Commissioning and Governance. Aim of Activity *. Implement the new South Western Sydney regional mental health and suicide prevention plan to 2030 to achieve a more integrated service system and improve mental health outcomes for consumers.. Description of Activity *. Implement the new South Western Sydney regional mental health and suicide prevention plan to 2030, in joint partnership with South Western Sydney Local Health District. Establish governance to oversee this activity and mechanisms to monitor progress. Implementation will involve collaboration with consumers, primary care professionals and service providers.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Mental health; 171. Alcohol and other drugs; 171... Activity Demographics... Target Population Cohort. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 30/06/2017. Activity End Date. 29/06/2026. Service Delivery Start Date. Service Delivery End Date. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. Yes. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Consultation occurred for development of the new plan in 2025.. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |

|  | NAB-UAS - 1 - Universal Aftercare Services... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-UAS. Activity Number *. 1. Activity Title *. Universal Aftercare Services. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Mental Health Priority Area 5: Community based suicide prevention activities. Other Program Key Priority Area Description. Aim of Activity *. Commission non-clinical aftercare services to improve health outcomes for individuals following a suicide attempt and/or suicidal crisis: and ensure consistent and best practice support. Establish Local Community Collaboratives.. Description of Activity *. Continue to commission non-clinical aftercare services. Based on the outcome of state-wide codesign, transition The Way Back Support Service to the Universal Aftercare model specified by the NSW Ministry of Health and Australian Government by July 2025. Scale-up existing or commission a new universal aftercare service to work alongside existing, to address unmet needs of identified priority populations, increase accessibility and improve quality by July 2025. Administer local community collaboratives in suicide prevention and deliver suicide prevention training to the community and service providers.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Mental health; 171... Activity Demographics... Target Population Cohort. Individuals following a suicide attempt and/or suicidal crisis.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. SWSPHN undertook co-design for suicide prevention, aftercare, and postvention in 2023-24 FY.. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 30/04/2023. Activity End Date. 29/06/2027. Service Delivery Start Date. 01/07/2023. Service Delivery End Date. 30/06/2027. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: Yes Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: Yes Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. Yes. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. Yes. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Wayback service provider has been decommissioned.. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |
| --- | --- | --- |

|  | NAB-UAS-Ops - 0 - Universal Aftercare Services - Operational Funding... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-UAS-Ops. Activity Number *. 0. Activity Title *. Universal Aftercare Services - Operational Funding. Existing, Modified or New Activity *. New Activity. Activity Priorities and Description... Program Key Priority Area *. Other Program Key Priority Area Description. Aim of Activity *. Description of Activity *. Needs Assessment Priorities *. Needs Assessment. Priorities. Activity Demographics... Target Population Cohort. In Scope AOD Treatment Type *. Indigenous Specific *. Indigenous Specific Comments. Coverage. Whole Region. Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. Activity End Date. Service Delivery Start Date. Service Delivery End Date. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. Is this activity the result of a previous co-design process?. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. Has this activity previously been co-commissioned or joint-commissioned?. Decommissioning. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |
| --- | --- | --- |

|  | NAB-HE - 2 - headspace Enhancement - Oran Park... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-HE. Activity Number *. 2. Activity Title *. headspace Enhancement - Oran Park. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Mental Health Priority Area 2: Child and youth mental health services. Other Program Key Priority Area Description. Aim of Activity *. The New South Wales Bilateral Schedule on Mental Health and Suicide Prevention (the Bilateral Schedule) sets out commitments from governments to reduce wait times and ensure young people aged 12-25 can access an appropriate level of support. This will be achieved through enhancement of the newly established headspace service – headspace Oran Park.. Description of Activity *. Provide additional funding to the new headspace Oran Park service, to support centre growth (including outreach at Narellan), manage demand and implement enhancement activities. Specific activities include increased clinical and non-clinical FTE (allied health (including family therapists) and clinical management and staffing to support the delivery of outreach services at Narellan Library and at schools across Camden LGA. Establishment of this centre has been delayed as per updates provided to DoHAC during 2023/24 FY and 2024/25 FY. Enhancement funding allocated in 2023/24 FY and 2024/25 FY will be rolled over to future financial years. 100% of funding will be allocated to this centre as the funds are quarantined and not able to be redistributed above the funding floor.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Mental health; 171. Alcohol and other drugs; 171... Activity Demographics... Target Population Cohort. Young people aged 12-25 years with mild to moderate mental health problems, including their families and friends.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. No. SA3 Name; SA3 Code. Camden; 12301... Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 30/04/2023. Activity End Date. 29/06/2026. Service Delivery Start Date. 01/07/2023. Service Delivery End Date. 30/06/2026. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |
| --- | --- | --- |

|  | NAB-HE - 3 - headspace Enhancement – Bankstown, Liverpool and Campbelltown... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-HE. Activity Number *. 3. Activity Title *. headspace Enhancement – Bankstown, Liverpool and Campbelltown. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Mental Health Priority Area 2: Child and youth mental health services. Other Program Key Priority Area Description. Aim of Activity *. The New South Wales Bilateral Schedule on Mental Health and Suicide Prevention (the Bilateral Schedule) sets out commitments from governments to reduce wait times and ensure young people aged 12-25 can access an appropriate level of support. This will be achieved through enhancement of existing headspace services including headspace Bankstown, Campbelltown and Liverpool.. Description of Activity *. Provide additional funding to existing headspace services in accordance with applicable funding floors, to support centre growth, manage demand and implement enhancement activities. Specific activities include increased clinical and non-clinical FTE (allied health (including family therapists), community development officers, centre managers, peer workers, youth access clinicians and administrative officers). Provide specialist training to staff and group development. Surplus enhancement funding will continue to be redistributed to headspace Liverpool as per 2025/26 FY to ensure equity and access across all SWS headspace services.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Mental health; 171. Alcohol and other drugs; 171... Activity Demographics... Target Population Cohort. Young people aged 12-25 years with mild to moderate mental health problems, including their families and friends.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. No. SA3 Name; SA3 Code. Bankstown; 11901. Liverpool; 12703. Campbelltown (NSW); 12302... Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 30/04/2023. Activity End Date. 29/06/2026. Service Delivery Start Date. 01/07/2023. Service Delivery End Date. 30/06/2026. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |
| --- | --- | --- |

|  | NAB-HE-Ops - 0 - headspace Enhancement - Operational Funding... Activity Metadata... Applicable Schedule *. NMHSPA Bilateral PHN Program. Activity Prefix *. NAB-HE-Ops. Activity Number *. 0. Activity Title *. headspace Enhancement - Operational Funding. Existing, Modified or New Activity *. New Activity. Activity Priorities and Description... Program Key Priority Area *. Other Program Key Priority Area Description. Aim of Activity *. Description of Activity *. Needs Assessment Priorities *. Needs Assessment. Priorities. Activity Demographics... Target Population Cohort. In Scope AOD Treatment Type *. Indigenous Specific *. Indigenous Specific Comments. Coverage. Whole Region. Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. Activity End Date. Service Delivery Start Date. Service Delivery End Date. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. Is this activity the result of a previous co-design process?. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. Has this activity previously been co-commissioned or joint-commissioned?. Decommissioning. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29... Totals. Funding Stream; FY 24 25; FY 25 26; FY 26 27; FY 27 28; FY 28 29; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Summary of activity changes for Department... Activity Status. Approved. Subject; Description; Commented By; Date Created... |  |
| --- | --- | --- |