This Model for Improvement (MFI) has been adapted from the Institute of Healthcare Innovation to develop, test and implement changes in general practices participating in South Western Sydney PHN’s Quality Improvement in Primary Care Program (QIPC). Following this plan can assist practices to meet the requirements from the Department of Health’s Practice Incentive Program Quality Improvement (PIP QI).

This model consists of three parts that are of equal importance to help guide the change(s) you would like to implement.

{

Session 1

Part 1: Identifying areas for improvement from POLAR reports & formulating sustainable solutions

Part 2: Developing an Improvement Plan to address the focus areas

{

Follow up

Part 3: Reviewing the Plan and considering your next steps

For support in the design and implementation of the Model for Improvement in your general practice contact us on 02 4632 3000 or speak to your Practice Support Officer / Practice Advancement Officer / Clinical and Quality Improvement Officer.

MFI Start Date: 20/10/2025    MFI Number:      5                Practice Name:    Apple Medical Centre

Part 1: Identify

| What area(s) for improvement have you identified |  | What are some sustainable solutions* to address the issue? * Sustainable solutions: an idea that will address the area(s)for improvement. E.g., changes to standard procedures or reviewing the issue quarterly |  |
| --- | --- | --- | --- |
| 1 | Area: Identify Potentially eligible patients for National Lung Cancer Screening Program (NLCSR) aged 50-70yo with a smoking history recorded Baseline: 550 patients | Solution 1 | Using POLAR to identify potentially eligible patients who are aged 50-70yo with a smoking history recorded |
|  |  | Solution 2 | To integrate practice software with National Cancer Screening Register (NCSR) |
|  |  | Solution 3 | Promote Lung cancer Screening |
|  |  | Solution 4 | Establish a robust recall/reminder system |
| 2 | Area: Baseline: | Solution 1 |  |
|  |  | Solution 2 |  |
|  |  | Solution 3 |  |

Part 2: Plan

| Select one or more of the solutions from Part 1 and design a plan to implement these. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Area(s) for Improvement |  | Solution Number(s) | What steps will you take to implement the solution(s)? |  | Person Responsible | Timeframe |
| 1 | Area: Identify potentially eligible patients for National Lung Cancer Screening Program aged 50-70yo with a smoking history recorded | 1,2,3,4 | Utilise POLAR to extract a list of potentially eligible patients with a history of smoking using this Walkthrough |  | QI champion/PHN staff | 1 day |
|  |  |  | Register with NCSR and enable integration with clinical software (MD/BP) |  | Practice manager | 1 week |
|  |  |  | Display promotional material about the NLCSP in our waiting room, and ensure all clinicians review NLCSP conversation guide and are adept at discussing all elements of the program with potentially eligible patients |  | Practice manager/QI champion | 1 month |
|  |  |  | Setting up a reminder (MD/BP) based on the data showing on the extracted patient list |  | Practice Nurse/ Admin team | Ongoing |
| 2 | Area: |  |  |  |  |  |
| Prediction(s): What outcome would you like to achieve? |  |  |  | Measures: How and where to measure the improvement? |  |  |
| Area 1: To review 100 patients on the extracted list and data cleanse any inactive patients |  |  |  | POLAR> Clinic Summary> Clinical Indicators> Inclusion Filters> Age rage> Smoking status |  |  |
| Area 2: |  |  |  |  |  |  |

Part 3: Review

| # Do: Was the plan executed? Document any barriers or challenges |  |  |
| --- | --- | --- |
| # Yes, the plan was executed with minimal issues except inactive patients taking up extra time to cleanse |  |  |
| # Study: Record, analyse and reflect on the results in the table below |  |  |
| # Area(s) for Improvement |  | # Analysis and reflection on the latest results # (Include the impact of working on these areas e.g. practice workflow, staff, patient, etc.) |
| 1 | Area: Identify Potentially eligible patients for National Lung Cancer Screening Program aged 50-70yo with a smoking history recorded Baseline: 550 patients Latest Result: 305 patients | # We have achieved our target and found that integrating the NCSR into our clinical software helped us to keep track. We also took extra time to set up an efficient recall/reminder system to enable us to be prepared for future/ongoing scans for our patients enrolled in the program. |
| 2 | Area: Baseline: Latest Result: |  |
| # Act: What is your next step or idea, and how might you apply what you learn? |  |  |
| # We will continue working on reviewing the entire list of patients, and we have updated our new patient forms to make it mandatory to answer all fields including smoking. Our nurses are regularly opportunistically asking patients when they have a consultation and updating old records(over 7 years old) to ensure our data is accurate. |  |  |

MFI End Date: 27/01/2026        MFI Completed By (Practice Staff Name):   Nurse Mabel