|  | South Western Sydney - Aged Care 2023/24 - 2027/28 Activity Summary View. |  |  |
| --- | --- | --- | --- |
|  | AC-EI - 3 - Early Intervention - Flex... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-EI. Activity Number *. 3. Activity Title *. Early Intervention - Flex. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. AC 3.1 Commission service provider to improve health literacy and access to social and wellbeing services for older people in Fairfield and Liverpool LGAs. AC 3.2 Reduce the risk of falls in older people via the use of targeted falls prevention programs.. Description of Activity *. AC 3.1 - Increased awareness in local primary health care workforce of the needs of older people and availability of our initiatives through variety of communication mechanisms. Including CPD, healthpathways, education and service directories. Establishment Phase 01/02/23 - 30/06/23: - Engage with community organisations within South Western Sydney region with a focus on Fairfield and Liverpool LGAs, supporting older people with chronic conditions. Older people and their family/carers will be invited to participate in co-design forums to ensure services are designed to enable older people to make changes to their current lifestyle to improve their overall health and wellbeing. Service delivery phase 01/07/23 - 30/06/26: - Facilitation of face-to-face educational workshops for older people in language as required. - - Community capacity building toward supporting older people to remain healthy at home, through education (including health literacy), connection and advocacy initiatives. - Use of validated outcome measures to ensure services are effective. - Development of HealthPathways to support primary care providers in the care of older people and Health Resource Directory fact sheets for consumers. AC 3.2 - Commission services to support falls prevention in older people in South Western Sydney.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aboriginal and Torres Strait Islander health; 22. Aged Care; 31... Activity Demographics... Target Population Cohort. - People aged 65 years and over. - Aboriginal and Torres Strait Islander people 50 years and older. - Cultural and Linguistically Diverse populations.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. - Consultation with community and service providers to identify gaps and needs in health and social services for older people in SWS region. - Aged Care Advisory Committee - SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services / residential aged care services and relevant PHN teams. - Healthy Ageing at Home webpage (HealthChat) has provided opportunities for community members to learn and receive updates on the project. - Participation by SWSPHN representatives at a variety of aged care forums, meetings, and conferences on an ongoing basis.. Collaboration. - Collaboration with range of stakeholders in both community, social and health sectors in the design, implementation and monitoring of the Healthy Ageing at Home project. - Participation and contribution to the NSW/ACT PHN Community of Practice for Aged Care, resulted in advocacy for advice on implementation of ICHOM tools within the Healthy Ageing at Home project. - Regular operational support meetings are undertaken in collaboration with commissioned services and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 28/11/2021. Activity End Date. 27/06/2026. Service Delivery Start Date. 01/01/2023. Service Delivery End Date. 31/12/2026. Other Relevant Milestones. - Consultation and Co-Design completed June 2022 - Tender completed and Board Approval October 2022 - Commissioned service provider commencing activity January 2023. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. Yes. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. During needs assessment co-design was integral in the design of the procurement plan. During implementation, co-design will be integral to understanding the model and service delivery mechanisms for older people from culturally and linguistically diverse communities.. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |

|  | AC-EI - 4 - Early Intervention - Operational... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-EI. Activity Number *. 4. Activity Title *. Early Intervention - Operational. Existing, Modified or New Activity *. Modified. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. AC 3.1 Improve health literacy and access to social and wellbeing services for older people in Fairfield and Liverpool LGAs. AC 3.2 Reduce the risk of falls in older people via the use of targeted falls prevention programs.. Description of Activity *. AC 3.1 - Increased awareness in local primary health care workforce of the needs of older people and availability of our initiatives through variety of communication mechanisms. Establishment Phase 01/02/23 - 30/06/23: - Engage with community organisations within South Western Sydney region with a focus on Fairfield and Liverpool LGAs, supporting older people with chronic conditions. Older people and their family/carers will be invited to participate in co-design forums to ensure services are designed to enable older people to make changes to their current lifestyle to improve their overall health and wellbeing. Service delivery phase 01/07/23 - 31/12/25: - Facilitation of face-to-face educational workshops for older people in language as required. - Community capacity building toward supporting older people to remain healthy at home, through education (including health literacy), connection and advocacy initiatives. - Development of HealthPathways to support primary care providers in the care of older people and Health Resource Directory fact sheets for consumers. AC 3.2 - Commission services to support falls prevention in older people in South Western Sydney.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aboriginal and Torres Strait Islander health; 22. Aged Care; 31... Activity Demographics... Target Population Cohort. - People aged 65 years and over. - Aboriginal and Torres Strait Islander people 50 years and older. - Cultural and Linguistically Diverse populations.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. - Consultation with community and service providers to identify gaps and needs in health and social services for older people in SWS region. - Aged Care Advisory Committee - SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services / residential aged care services and relevant PHN teams. - Healthy Ageing at Home webpage (HealthChat) has provided opportunities for community members to learn and receive updates on the project. - Participation by SWSPHN representatives at a variety of aged care forums, meetings, and conferences on an ongoing basis.. Collaboration. - Collaboration with range of stakeholders in both community, social and health sectors in the design, implementation and monitoring of the Healthy Ageing at Home project. - Participation and contribution to the NSW/ACT PHN Community of Practice for Aged Care, resulted in advocacy for advice on implementation of ICHOM tools within the Healthy Ageing at Home project. - Regular operational support meetings are undertaken in collaboration with commissioned services and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 28/11/2021. Activity End Date. 27/06/2025. Service Delivery Start Date. 01/01/2023. Service Delivery End Date. 31/12/2025. Other Relevant Milestones. - Consultation and Co-Design completed June 2022 - Tender completed and Board Approval October 2022 - Commissioned service provider commencing activity January 2023. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): Yes Other Approach (please provide details): No. Is this activity being co-designed?. Yes. Is this activity the result of a previous co-design process?. Yes. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-OSP - 5 - On-site Pharmacist Measure - RACHs... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-OSP. Activity Number *. 5. Activity Title *. On-site Pharmacist Measure - RACHs. Existing, Modified or New Activity *. New Activity. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. - Increase uptake of aged care on-site pharmacists by RACHs - Improve access to aged care on-site pharmacists in RACHs. Description of Activity *. - Identify eligible pharmacists who are available and eligible to work on-site in RACHs as part of the ACOP Measure - Disseminating information to RACHs about the ACOP Measure - Managing requests for support from RACHs regarding the ACOP measure including pharmacist matching - Support care coordination between RACH, general practitioner and pharmacist employed under the ACOP measure - Supporting communication and collaboration between ACOP pharmacists. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aged Care; 31... Activity Demographics... Target Population Cohort. - Pharmacist - RACH staff. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services/residential aged care services and relevant PHN teams (Digital Health).. Collaboration. Activities in Aged and Palliative Care are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 29/06/2024. Activity End Date. 28/06/2027. Service Delivery Start Date. Service Delivery End Date. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-VARACF - 1 - Virtual Access in RACFs - Flex... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-VARACF. Activity Number *. 1. Activity Title *. Virtual Access in RACFs - Flex. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. Support participating RACFs in the SWSPHN region to use appropriate virtual consultation technology so their residents can access clinically appropriate telehealth care with primary health care professionals.. Description of Activity *. - Assist participating RACHs in SWSPHN to have appropriate facilities and equipment to enable virtual consultations with primary care facilities, in line with eHealth standards e.g. ACRRM telehealth framework. - Provide training to RACH staff to support telehealth consultations. Webinars will be scheduled for RACH staff to participate in. The PHN is hosting our Connected Care Conference in August 2025 - virtual care will be a key theme of this conference which is tailored to GPs supporting RACHs. - Promote the use of enablers of digital health, e.g. MHR. PHN staff will work with the RACH staff and attending GPs to highlight the usability and utility of My Health Record in obtaining health information including reports, medications and discharge summaries. - Consult and plan with jurisdictional authorities to ensure initiatives are complementary and do not duplicate existing efforts underway to improve technological interoperability. - In providing funding to RACHs to support enhanced telehealth capabilities, continue to ensure robust commissioning framework principles are upheld, specifically focused on value for money, probity, and transparency. - HealthDirect Video Call accounts have been established for the RACHs who agreed to participate. This will occur for other RACHs who wish to participate. - Hardware kits have been funded and delivered for most RACFs. These will be available for the remaining 2 facilities if they wish to participate. - SWSPHN is exploring provisioning lightweight hardware for GPs actively visiting RACHs across the catchment. This activity will not commence without a formal business case submission to DHDA where formal approval to proceed will be requested with evidence provided following consultation/feedback from GPs and RACHs regarding meaningful use of video telehealth.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Digital health; 69. Aged Care; 31... Activity Demographics... Target Population Cohort. RACF residents, RACF staff, SWSLHD clinicians, GPs in SWSPHN catchment, practice nurses in SWSPHN catchment, specialists and allied health professionals in SWSPHN catchment.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. - Consult and plan with jurisdictional authorities to ensure initiatives are complementary and do not duplicate existing efforts underway to improve technological interoperability. - Needs assessment to understand telehealth capability.. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 27/06/2021. Activity End Date. 26/06/2026. Service Delivery Start Date. 01/07/2021. Service Delivery End Date. 30/06/2026. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): Yes Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-VARACF - 1 - Virtual Access in RACFs - Operational... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-VARACF. Activity Number *. 1. Activity Title *. Virtual Access in RACFs - Operational. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. Support participating RACFs in the SWSPHN region to use appropriate virtual consultation technology so their residents can access clinically appropriate telehealth care with primary health care professionals.. Description of Activity *. - Assist participating RACFs in SWSPHN to have appropriate facilities and equipment to enable virtual consultations with primary care facilities, in line with eHealth standards e.g. ACRRM telehealth framework. - Provide training to RACF staff to support telehealth consultations. - Promote the use of enablers of digital health, e.g. MHR.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Digital health; 69. Aged Care; 31... Activity Demographics... Target Population Cohort. RACF residents, RACF staff, SWSLHD clinicians, GPs in SWSPHN catchment, practice nurses in SWSPHN catchment, specialists and allied health professionals in SWSPHN catchment.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. Collaboration. Activity Milestone Details/Duration... Activity Start Date. 27/06/2021. Activity End Date. 26/06/2024. Service Delivery Start Date. 01/07/2021. Service Delivery End Date. 30/06/2025. Other Relevant Milestones. - Training provided to all participating RACFs: ongoing - Connected Care Conference: August 2025. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): Yes Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-CF - 2 - Care Finder Program... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-CF. Activity Number *. 2. Activity Title *. Care Finder Program. Existing, Modified or New Activity *. Modified. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. Maintain commissioned services to support targeted populations of older people to understand and access aged care and connect with relevant supports including a centralised referral point.. Description of Activity *. AC 2.1 Maintain focus on the identification of gaps and needs in health and social service access and navigation for older people in SWS region. AC 2.2 Support and monitor performance of the five commissioned service providers working to provide care finder services, across all seven SWS LGAs including to underserviced groups such as Aboriginal people, older people with a disability, and those at risk of homelessness. AC 2.3 Support and monitor performance of two of the six commissioned services working with a focus on CALD populations. AC 2.4 Support commissioned centralised intake service to embed the receival of referrals from community, external stakeholders, primary care and Local Health District services and assignment to the most appropriate care finder service and monitor contract performance. AC 2.5 Maintain established Community of Practice with care finder services and relevant stakeholders to support shared learnings, timely resolution of issues and collegiality between care finder service providers in the SWS region. AC 2.6 Commission service specialising in supporting Aboriginal community members to supplement access provided via Elder Care Support.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aged Care; 31... Activity Demographics... Target Population Cohort. People who are eligible for aged care services and have one or more reasons for requiring intensive support to: - Interact with My Aged Care and access aged care services and/or - Access other relevant supports in the community. Eligibility people are: - People aged 65 years and over. - Aboriginal and Torres Strait Islander people 50 years and older. - People with premature ageing: - 50+ years for non-Aboriginal and Torres Strait Islander people. - 45+ for Aboriginal and Torres Strait Islander people.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services / residential aged care services and community organisations supporting CALD, Disability and Aboriginal people.. Collaboration. Care finder activities are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services, aged care service providers and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 29/06/2025. Activity End Date. 28/06/2029. Service Delivery Start Date. 01/01/2025. Service Delivery End Date. 30/06/2029. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): Yes. Is this activity being co-designed?. Yes. Is this activity the result of a previous co-design process?. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. Yes. Decommissioning details?. Not renewing the contract with one former ACH provider.. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-CF - 2 - Care Finder Program - Operational... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-CF. Activity Number *. 2. Activity Title *. Care Finder Program - Operational. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. Maintain commissioned services to support targeted populations of older people to understand and access aged care and connect with relevant supports including a centralised referral point.. Description of Activity *. AC 2.1 Maintain focus on the identification of gaps and needs in health and social service access and navigation for older people in SWS region. AC 2.2 Support and monitor performance of the six commissioned service providers working to provide care finder services, across all seven SWS LGAs including to underserviced groups such as Aboriginal people, older people with a disability, and those at risk of homelessness. AC 2.3 Support and monitor performance of two of the six commissioned services working with a focus on CALD populations. AC 2.4 Support commissioned centralised intake service to embed the receival of referrals from community, external stakeholders, primary care and Local Health District services and assignment to the most appropriate care finder service and monitor contract performance. AC 2.5 Maintain established Community of Practice with care finder services and relevant stakeholders to support shared learnings, timely resolution of issues and collegiality between care finder service providers in the SWS region.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aged Care; 31... Activity Demographics... Target Population Cohort. People who are eligible for aged care services and have one or more reasons for requiring intensive support to: - Interact with My Aged Care and access aged care services and/or - Access other relevant supports in the community. Eligibility people are: - People aged 65 years and over. - Aboriginal and Torres Strait Islander people 50 years and older. - People with premature ageing: - 50+ years for non-Aboriginal and Torres Strait Islander people. - 45+ for Aboriginal and Torres Strait Islander people.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services / residential aged care services and community organisations supporting CALD, Disability and Aboriginal people.. Collaboration. Care finder activities are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services, aged care service providers and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 28/05/2022. Activity End Date. 27/06/2025. Service Delivery Start Date. 03/01/2023. Service Delivery End Date. 30/06/2025. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: Yes Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. Yes. Is this activity the result of a previous co-design process?. Yes. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |

|  | AC-AHARACF - 4 - After Hours Access in RACFs... Activity Metadata... Applicable Schedule *. Aged Care. Activity Prefix *. AC-AHARACF. Activity Number *. 4. Activity Title *. After Hours Access in RACFs. Existing, Modified or New Activity *. Existing. Activity Priorities and Description... Program Key Priority Area *. Aged Care. Other Program Key Priority Area Description. Aim of Activity *. Support improvement in after-hours service delivery to RACFs.. Description of Activity *. - To complete audits of RACH after-hours procedures for referral to After Hour services. Audit will also include review of the need to update these plans. - Provide advice and support on available after-hours supports within the region and how to access these. - Provide advice and support on policy development for after-hours processes within the RACF. - Provide support and education re: clinical documentation and digital medical record management. - Support engagement between RACH and treating GPs regarding after-hours planning, including assistance with troubleshooting issues.. Needs Assessment Priorities *. Needs Assessment. SWSPHN Needs Assessment 2025-2028. Priorities. Priority; Page reference. Aged Care; 31... Activity Demographics... Target Population Cohort. - People aged 65 years and over. - Aboriginal and Torres Strait Islander people 50 years and older.. In Scope AOD Treatment Type *. Indigenous Specific *. No. Indigenous Specific Comments. Coverage. Whole Region. Yes. Activity Consultation and Collaboration... Consultation. SWSPHN maintains engagement and consultation activities on an ongoing basis with community representatives, GPs, the Local Health District, community aged care services/residential aged care services and relevant PHN teams (Digital Health).. Collaboration. Activities in Aged and Palliative Care are undertaken in collaboration with residential aged care, General Practice, NSW Ambulance, relevant LHD services and other key stakeholders as necessary.. Activity Milestone Details/Duration... Activity Start Date. 27/12/2021. Activity End Date. 27/12/2026. Service Delivery Start Date. Service Delivery End Date. Other Relevant Milestones. Activity Commissioning... Please identify your intended procurement approach for commissioning services under this activity:. Not Yet Known: No Continuing Service Provider / Contract Extension: No Direct Engagement: No Open Tender: No Expression Of Interest (EOI): No Other Approach (please provide details): No. Is this activity being co-designed?. No. Is this activity the result of a previous co-design process?. No. Do you plan to implement this Activity using co-commissioning or joint-commissioning arrangements?. No. Has this activity previously been co-commissioned or joint-commissioned?. No. Decommissioning. No. Decommissioning details?. Co-design or co-commissioning comments. Activity Planned Expenditure... Planned Expenditure. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28... Totals. Funding Stream; FY 23 24; FY 24 25; FY 25 26; FY 26 27; FY 27 28; Total... Funding From Other Sources - Financial Details. Funding From Other Sources - Organisational Details. Activity Comments... Activity Status. Submitted. PHN Comments. Subject; Description; Commented By; Date Created... Comments from the Department... Comment; Date Created. .; 22/07/2025... |  |
| --- | --- | --- |